## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | 2215-swen-261-05-5e

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | S.M; 03/8/2022 | Pass | S.W.; 3/29/2022; not sure where the Product page is and how to navigate on and off it
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | S.M; 03/8/2022 | Pass | S.W.; 3/29/2022; not sure where the Product page is and how to navigate on and off it
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | S.M; 03/8/2022 | Pass | S.W.; 3/29/2022
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | S.M; 03/8/2022 | Pass | S.W.; 3/29/2022
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | S.M; 03/15/2022 | Pass | S.W.; 3/29/2022
As a student I want to modify my shopping cart so that I can buy all courses I want to buy at the same time | Given when I am viewing a course, when I hit the "Add to Cart" button, then I expect the course to be added to my cart. | Pass | C.J; 03/15/2022 | Pass | C.G.; 3/29/2022
| Given when I am viewing my shopping cart, when I hit the remove button next to the course, then I expect the course to be removed from my shopping cart. | Pass | C.J; 03/15/2022 | Pass | C.G.; 3/29/2022; bug where items that admin delete is still in cart and messes up the whole cart
| Given when I am on the main page, when I hit the shopping cart button, then I expect to be shown the courses that are in my cart. | Pass | C.J; 03/15/2022 | Pass | C.G.; 3/29/2022
As a user I want to sign in so that I can interact with the elements of the site I am allowed to. | Given that the user want to sign in when buying courses then to sign in the user. | Pass | R.K C; 03/13/2022 | Pass | C.G.; 3/29/2022
As a user I want to be able search and filter through courses, so that I can find the course I am looking for faster. | Given that the course exists when a user types something into the search bar then, the list of courses on the page will be filtered by name and decription. | Pass | S.M; 03/8/2022 | Pass | C.G.; 3/29/2022
As a User I want an account so that I can save all the courses I bought. | Given a user wants a account when they sign up then an account should be created and saved. | Pass | R.K C; 02/28/2022 | Pass | C.G.; 3/29/2022
As an Admin I want to add a course so that students can purchase the course. | Given that an admin wants to add a course for a student to view/buy, when the admin adds a course to a website then students are able to view and purchase courses after they are added. | Pass | H.D; 03/11/2022 | Pass | C.G.; 3/29/2022
As an Admin I want to update courses so that the courses contain up-to-date information. | Given that an admin wants to update an existing course, when the admin updates a course on the website thenstudents are able to see the updated version of the course. | Pass | H.D; 03/11/2022 | Pass | C.G.; 3/29/2022
As an Admin I want to delete courses so that out-of-date or problematic courses can be removed from the site. | Given a course exists, when I hit the delete button, then I expect a confirm dialog | Pass | H.D; 03/11/2022 | Fail | C.G.; 3/29/2022; no dialog when deleted
| Given the confirm dialog exists, when I hit confirm, the course is deleted from the course database | Pass | H.D; 03/11/2022 | Fail | C.G.; 3/29/2022; no dialog when deleted
| Given that I am signed in as an ADMIN, when I view the course list, then I expect to see delete buttons next to each course. | Pass | H.D; 03/11/2022 | Pass | C.G.; 3/29/2022
As a Authenticated User I want to have My Own Page so that I can View purchased Courses and Edit my information. | Given an Authenticated user when I click user name then I WANT TO BE TAKEN TO AN UNIQUE USER PAGE. |  | sprint 3 | Pass | R.K.C; 03/27/2022
| Given USER IN THEIR PAGE when WHEN THEY CLICK ON THEIR PURCHASED COURSES then I WANT THEN TO BE TAKEN TO THE COURSE PAGE. |  | sprint 3 | Pass | R.K.C; 03/27/2022
As a USER I want to view the content of courses so that I can decide whether to buy the course or not. | Given a user is on the e-strore page, when the user clicks on the course title, details to the course should be revealed. |  | sprint 3 | Pass | S.M; 03/26/2022
| Given a user is on the course page and not signed in when the user clicks on the course lesson then they are taken to the login page. |  |  | Pass | S.M;03/26/2022
| Given a user is on the course page, signed in, and purchased the course when the user clicks on the course lesson a lesson video is played. |  |  | Pass | C.G.; 3/29/2022
| Given a user is on the course page, signed in, and did not purchase the course, when the user clicks on the course lesson, they are prompted to buy the course first. |  |  | Fail | C.G.; 3/29/2022. No promt to purchase when not brought
As an Admin I want to add lessons to my course creation | Given that the admin wants to add a lesson to a course when a admin fills out the lesson form and hits submit then a new lesson is added to the course. |  | sprint 3 | Pass | H.D; 03/26/2022
As an Admin I want to block a student so that I can protect the site**. | Given the admin wants to block a student when the admin blocks a student then the student is no longer able to sign in. |  | sprint 3 |  | //not implemented
As a student, I want to be recommended courses with tags similar to courses I have bought before so that I am more likely to buy courses in the future | Given I have bought courses in the past with a certain tag, when I go to browse courses, I expect to see other courses with the same tag. |  | sprint 3 |  | //not implemented
| Given I have not bought courses in the past, when I go to browse courses, I expect to see the most popular courses that other people have bought. |  |  | Pass | C.J; 03/25/2022
As a USER, I want to be recommended courses based on the most popular courses that other users have bought so that I am more likely to create a student account and buy a course. | Given I have not bought courses in the past, when I go to browse courses, I expect to see the most popular courses that other people have bought. |  | sprint 3 | Pass | C.J; 03/25/2022
As a USER I want to not be able to enter malicious usernames so that the website does not get hacked. | Given a user trying to sign in, when a user doesn't input alphnemeric characters as a username then they are prompted with an error. |  | sprint 3 | Pass | C.G; 03/29/2022
As a Student I want to be able to checkout courses in my cart so that I can buy several courses at once. | Given I have courses in the shopping cart, when I look next to the checkout button, I expect to see the total price of all courses in the shopping cart. |  | sprint 3 |  | //not implemented
| Given I have courses in the shopping cart, when I press the checkout button, then I expect to have those courses removed from the shopping cart and added to purchased courses |  |  |  | //not implemented
Given a user purchased the course when the user goes to their page then the purchaced course(s) should be their.